מערכת ניהול לו"ז פרויקטי בינוי ושיפוץ

PMO-OVERWATCAH

Construction & Renovation Project Schedule Management System

Functional Specification — Phase 1 Development

Version 1.0  |  April 2026

GUIDING PRINCIPLE

Simplicity · Uniformity · Usability · Strong multi-project oversight

Table of Contents

1.  System Purpose & Scope	3

2.  Design Principles	3

3.  User Roles, Authentication & Permissions	4

4.  Project Data Model	6

5.  Topic 1 – Asset Identification & Approval	7

6.  Topic 2 – Planning	8

7.  Topic 3 – Tenders	9

8.  Topic 4 – Execution to Occupancy	10

9.  Topic 5 – Approvals & Occupancy	11

10.  Topic 6 – Post-Occupancy	12

11.  Schedule & Date Model	13

12.  Status Calculation Rules	14

13.  Delay Reasons & Project Freeze	15

14.  Contractors	16

15.  Mandatory Update Fields	16

16.  Key Milestone Logic	17

17.  Screens & Views	17

18.  Weekly Snapshot	22

19.  Design System (UI/UX)	23

20.  Phase 2 Backlog	25

1.  System Purpose & Scope

## 1.1  Purpose

This system is designed exclusively for schedule management of construction, renovation, occupancy, and asset-return projects. It is not a detailed task-management tool for individual project managers or contractors — its purpose is senior multi-project oversight.

## 1.2  Four Core Needs

- Ongoing management control over project status

- Identification of deviations and risks

- Support for the weekly review discussion

- Forward view of upcoming milestones (30-day horizon)

## 1.3  Explicitly Out of Scope — Phase 1

| Out of Scope | Notes |
| --- | --- |
| Budget management | Phase 2 candidate |
| Financial contracts | Phase 2 candidate |
| Document management | Phase 2 candidate |
| Detailed task management | Not a PM tool for contractors |
| Resource management | Phase 2 candidate |
| Full quality control | Phase 2 candidate |
| Work log / timesheets | Phase 2 candidate |

## 1.4  Scale

The system must support up to 50 active projects running concurrently. Phase 1 uses a single uniform project type.

2.  Design Principles

| Principle | Definition |
| --- | --- |
| Simplicity over completeness | Prefer a simpler model to guarantee actual usage, reporting discipline, easy maintenance, and fast development. |
| Four-level hierarchy | Project → Main Topic → Domain / Sub-topic (as needed) → Milestone |
| Single source of truth | Project Manager owns update responsibility. PMO owns templates, openings, exceptions, and control. |
| Uniformity with controlled flexibility | Fixed structure, fixed lists, fixed templates by default. "Not Relevant" flag is always available. Exceptions added by PMO only. |

3.  User Roles, Authentication & Permissions

## 3.1  Authentication — Google OAuth 2.0

All users authenticate via Google Sign-In (OAuth 2.0). There are no local passwords. The Admin activates accounts and assigns roles after a user's first login attempt.

📌  New users who sign in with Google are placed in a PENDING state until an Admin approves their account and assigns a role. Pending users cannot access any system data.

## 3.2  Role Summary

| Role (Hebrew) | Role (English) | Count | Can Edit |
| --- | --- | --- | --- |
| אדמין (Admin) | System Administrator | Unlimited | Full — including user management |
| PMO | PMO Controller | Unlimited | All projects, templates, weekly snapshot |
| מנהל פרויקט | Project Manager | Unlimited | Own assigned projects only |
| צפייה בלבד | View Only (Management) | Unlimited | None — dashboard & reports only |

## 3.3  Admin Capabilities

- Access user management screen (Screen 7 — see Section 17)

- View all pending registration requests from Google Sign-In

- Approve or reject pending users

- Assign role to each approved user: PMO / Project Manager / View Only

- Deactivate (soft-delete) any user account

- Reassign projects when a Project Manager changes

- Reset any user's role at any time

## 3.4  Detailed Permission Matrix

| Capability | Admin | PMO | Proj. Mgr. | View Only |
| --- | --- | --- | --- | --- |
| Open / create new project | ✓ | ✓ | ✗ | ✗ |
| Edit any project | ✓ | ✓ | ✗ | ✗ |
| Edit own assigned projects | ✓ | ✓ | ✓ | ✗ |
| Update Forecast | ✓ | ✓ | ✓ | ✗ |
| Update Actual dates | ✓ | ✓ | ✓ | ✗ |
| Update statuses | ✓ | ✓ | ✓ | ✗ |
| Update notes / delay reasons / freezes | ✓ | ✓ | ✓ | ✗ |
| Manually select key exception milestone | ✓ | ✓ | ✓ | ✗ |
| Manage default lists & templates | ✓ | ✓ | ✗ | ✗ |
| Add structure exceptions | ✓ | ✓ | ✗ | ✗ |
| Save weekly snapshot | ✓ | ✓ | ✗ | ✗ |
| View dashboard & reports | ✓ | ✓ | ✓ | ✓ |
| Manage users (approve / assign roles) | ✓ | ✗ | ✗ | ✗ |
| Deactivate users | ✓ | ✗ | ✗ | ✗ |

## 3.5  Session & Security

- Sessions persist for 8 hours; the user is prompted to re-authenticate after expiry.

- All API calls carry a JWT signed by Google. The backend validates the token on every request.

- Deactivated users are immediately blocked even if they hold a valid token.

- The system does not store Google passwords. Only the Google user ID and email are stored.

4.  Project Data Model

## 4.1  Mandatory Fields — Project Opening

| # | Field (Hebrew) | Field (English) | Type / Source |
| --- | --- | --- | --- |
| 1 | קוד פרויקט | Project Code | Auto-generated |
| 2 | שם פרויקט | Project Name | Manual text |
| 3 | מנהל פרויקט פנימי | Internal Project Manager | User list (role = PM) |
| 4 | אחראי פרויקט פנימי נוסף | Additional Internal Owner | User list |
| 5 | צפי קבלת נכס | Expected Asset Receipt Date | Date picker |
| 6 | יעד אכלוס | Occupancy Target | Date picker |
| 7 | רמת עדיפות | Priority Level | Dropdown: High / Medium / Low |

## 4.2  Additional Project-Level Fields

| Field (Hebrew) | Field (English) | Source |
| --- | --- | --- |
| אדריכל | Architect | Managed list |
| מנהל פרויקט / מפקח חיצוני | External PM / Supervisor | Managed list |
| סטטוס פרויקט מחושב | Computed Project Status | Calculated (see §12) |
| תאריך עדכון אחרון | Last Updated Date | Auto — system timestamp |
| לא עודכן השבוע | Not Updated This Week | Calculated |
| נדרש טיפול הנהלה | Requires Management Action | Calculated + manual override |
| סטטוס הקפאה / סיבה / הערה | Freeze Status / Reason / Note | Manual (see §13) |
| תאריך פתיחה במערכת | System Open Date | Auto — creation timestamp |
| קבלנים שנבחרו | Selected Contractors | Structured list (see §14) |

## 4.3  Critical Assignment Rules

📌  These rules generate warnings in the system but do not hard-block saves.

- Architect must be assigned by milestone: "Programme & Feasibility Study"

- Internal Project Manager must be assigned by milestone: "Engineering Survey & Technical Spec"

- External PM / Supervisor (if applicable) must be assigned by milestone: "Engineering Survey & Technical Spec"

## 4.4  Project Structure — 6 Main Topics

| # | Topic (Hebrew) | Topic (English) | Affects Main Status? |
| --- | --- | --- | --- |
| 1 | איתור ואישור נכס ופרויקט | Asset Identification & Project Approval | Yes |
| 2 | תכנון | Planning | Yes |
| 3 | מכרזים | Tenders | Yes |
| 4 | ביצוע עד לאכלוס | Execution to Occupancy | Yes |
| 5 | אישורים ואכלוס | Approvals & Occupancy | Yes |
| 6 | אחרי האכלוס | Post-Occupancy | No (post-project) |

Project completion is defined as: actual occupancy entry (Topic 5, milestone 11). Topic 6 is tracked independently and does not affect the main project status.

5.  Topic 1 — Asset Identification & Project Approval

Milestones (sequential tracking, no sub-domains):

| # | Milestone (Hebrew) | Milestone (English) |
| --- | --- | --- |
| 1 | איתור נכס | Asset Identification |
| 2 | פרוגרמה ובדיקת התכנות | Programme & Feasibility Study |
| 3 | מינוי מנהל פרויקט חיצוני | Appointment of External PM |
| 4 | מינוי אדריכל | Appointment of Architect |
| 5 | סיור הנדסי ומפרט טכני | Engineering Survey & Technical Spec |
| 6 | סיור הנהלה | Management Site Visit |
| 7 | שמאות | Valuation / Appraisal |
| 8 | מסמך החלטה ואישור פורמלי | Decision Document & Formal Approval |
| 9 | חתימת חוזה | Contract Signing |

6.  Topic 2 — Planning

## 6.1  Structure

- General milestones (topic-level workflow)

- Planning domains (per discipline)

- Sub-domain: Appointment of Consultants / Designers

## 6.2  General Workflow Milestones

| # | Milestone (Hebrew) | Milestone (English) |
| --- | --- | --- |
| 1 | אישור ועדה לאישור תוכניות | Planning Committee Approval |
| 2 | מדידה | Survey / Measurement |
| 3 | מינוי יועצים / מתכננים | Appointment of Consultants / Designers |
| 4 | תכנון מפורט לפי תחומים | Detailed Planning by Domain |
| 5 | השלמת אינטגרציה של תוכניות | Integration of All Consultant Plans |
| 6 | כתבי כמויות לפי תחומים | Bills of Quantities by Domain |

## 6.3  Planning Domains (Fixed)

| # | Domain (Hebrew) | Domain (English) | Phases per Domain |
| --- | --- | --- | --- |
| 1 | אדריכלות | Architecture | Detailed design + Bill of Quantities |
| 2 | חשמל | Electrical | Detailed design + Bill of Quantities |
| 3 | אינסטלציה | Plumbing & Sanitation | Detailed design + Bill of Quantities |
| 4 | מיזוג אוויר | HVAC | Detailed design + Bill of Quantities |
| 5 | נגרות | Carpentry / Joinery | Detailed design + Bill of Quantities |
| 6 | מיתוג ושילוט | Branding & Signage | Detailed design + Bill of Quantities |

## 6.4  Consultant Appointment Sub-Domain

| # | Role (Hebrew) | Role (English) | Default Status |
| --- | --- | --- | --- |
| 1 | נגישות | Accessibility Consultant | Required |
| 2 | בטיחות | Safety Consultant | Required |
| 3 | חשמל | Electrical Engineer | Required |
| 4 | מיזוג אוויר | HVAC Engineer | Required |
| 5 | קונסטרוקטור | Structural Engineer | Required |
| 6 | אדריכל | Architect | Required |
| 7 | מיתוג | Branding Consultant | Required |
| 8 | מנהל פרויקט / מפקח | PM / Supervisor | Required |
| 9 | אינסטלציה | Plumbing Engineer | Required |
| 10 | כמאי | Quantity Surveyor | Required |

Each consultant role can be marked: Assigned (name from managed list) or Not Relevant.

## 6.5  Topic 2 Completion Conditions

📌  All four conditions must be met for Topic 2 to be marked Complete.

- All relevant planning domains completed

- Consultant integration milestone completed

- All relevant Bills of Quantities completed

- All relevant consultant roles filled

7.  Topic 3 — Tenders

## 7.1  Tender Domains (Fixed Default)

| # | Tender Domain (Hebrew) | Tender Domain (English) |
| --- | --- | --- |
| 1 | בינוי, חשמל ואינסטלציה | Construction, Electrical & Plumbing |
| 2 | מיזוג אוויר | HVAC |
| 3 | ריהוט | Furniture |
| 4 | מיתוג ושילוט | Branding & Signage |

## 7.2  Stages per Tender Domain (Fixed)

| # | Stage (Hebrew) | Stage (English) |
| --- | --- | --- |
| 1 | פרסום | Publication |
| 2 | קבלת הצעות | Receipt of Proposals |
| 3 | מו"מ | Negotiation |
| 4 | אישור ועדת התקשרויות | Procurement Committee Approval |

## 7.3  Rules

- No general "go-to-tender" approval milestone — each domain manages its own stages.

- Any tender domain can be marked Not Relevant.

- Adding a new tender domain requires PMO authorization.

- Topic 3 is complete when all relevant tender domains are completed.

8.  Topic 4 — Execution to Occupancy

## 8.1  Milestones (Single flat list, no sub-domains)

| # | Milestone (Hebrew) | Milestone (English) |
| --- | --- | --- |
| 1 | חתימה והתארגנות קבלן | Contractor Signing & Mobilization |
| 2 | ביצוע מערכות בתקרה | Ceiling Systems Execution |
| 3 | סגירת תקרה | Ceiling Closure |
| 4 | ריצוף | Flooring |
| 5 | שירותים | Restrooms |
| 6 | מטבח | Kitchen |
| 7 | לוח חשמל | Electrical Panel |
| 8 | ריהוט | Furniture |
| 9 | תשתיות תקשורת | Communications Infrastructure |
| 10 | תשתיות בטחון | Security Infrastructure |
| 11 | חדר מוגן | Safe Room |
| 12 | התקנת מכשירים לשירות עצמי | Self-Service Device Installation |
| 13 | שילוט חוץ | External Signage |
| 14 | מיתוג פנים | Interior Branding |
| 15 | צמחיה | Landscaping / Plants |
| 16 | אספקת כיסאות | Chair Delivery |
| 17 | אספקת ציוד למטבח | Kitchen Equipment Delivery |
| 18 | מסירה פנימית מוכנה לאישורים | Internal Handover Ready for Approvals |

## 8.2  Special Rules

- "Contractor Signing & Mobilization" can only be marked Complete if: (a) a relevant contractor is selected AND (b) an actual date is entered.

- "Internal Handover Ready for Approvals" is entered manually and is a mandatory completion condition for Topic 4.

- Any milestone can be marked Not Relevant.

- Adding new milestones requires PMO authorization.

9.  Topic 5 — Approvals & Occupancy

## 9.1  Milestones

| # | Milestone (Hebrew) | Milestone (English) | Mandatory Pre-Occupancy? |
| --- | --- | --- | --- |
| 1 | אישור יועץ בטיחות | Safety Consultant Approval | ✓ Yes |
| 2 | אישור כיבוי אש | Fire Department Approval | No |
| 3 | אישור נגישות | Accessibility Approval | No |
| 4 | אישור פיקוח | Supervision Approval | No |
| 5 | אישור מתכנן מיזוג אוויר | HVAC Designer Approval | No |
| 6 | אישור מתכנן חשמל | Electrical Designer Approval | No |
| 7 | אישור אדריכל | Architect Approval | No |
| 8 | אישור אכלוס עירייה | Municipal Occupancy Permit | ✓ Yes |
| 9 | משלוח הודעות ללקוחות | Customer Notifications Sent | ✓ Yes |
| 10 | פרסום מכתב הוראות ביצוע פנים-ארגוני | Internal Execution Instructions Published | ✓ Yes |
| 11 | כניסה בפועל לאכלוס | Actual Occupancy Entry | N/A — this IS completion |

📌  Milestone 11 "Actual Occupancy Entry" is entered manually and marks the project as complete. The 4 prerequisites (marked Yes) must be completed before it can be entered.

## 9.2  Topic 5 Completion Condition

- All relevant milestones completed AND

- Actual Occupancy Entry recorded

10.  Topic 6 — Post-Occupancy

Topic 6 does not affect the main project status. It is tracked for internal review discussions only.

## 10.1  Sub-Topics

| # | Sub-Topic (Hebrew) | Sub-Topic (English) | Default |
| --- | --- | --- | --- |
| 1 | מסירה ותיעוד | Handover & Documentation | Required |
| 2 | ליקויים ובדק | Defects & Warranty | Required |
| 3 | העברה לאחזקה | Transfer to Maintenance | Required |
| 4 | סגירה ניהולית | Administrative Closure | Required |
| 5 | החזרת נכס קודם | Return of Previous Asset | Required (unless N/A) |

## 10.2  Previous Asset Return — Milestones

| # | Milestone (Hebrew) | Milestone (English) |
| --- | --- | --- |
| 1 | תיאום פינוי | Evacuation Coordination |
| 2 | תיקונים / השבה למצב נדרש | Repairs / Restoration to Required Condition |
| 3 | מסירה לגורם מקבל / בעל נכס | Handover to Receiving Party / Asset Owner |

11.  Schedule & Date Model

## 11.1  Primary Anchor

Expected Asset Receipt Date — entered at project opening; the scheduling template is anchored to this date.

## 11.2  Schedule Resolution — Phase 1

📌  Dates are managed at the Main Topic level only. Individual milestones do not have auto-calculated target dates.

| Level | Has Target Date? | Has Forecast? | Has Actual? | Auto-Calculated? |
| --- | --- | --- | --- | --- |
| Project (Occupancy) | Yes (manual) | Yes (manual) | Yes (manual) | No |
| Main Topic | Yes (original) | Yes (editable) | Yes (actual) | Original: system default; changes: manual |
| Milestone | Optional (manual) | Optional (manual) | Yes (manual) | No |

## 11.3  Manual Change Rules

- Any manual change is local — it does not cascade to other topics or milestones.

- Changeable fields: Expected Asset Receipt Date, Occupancy Target, Topic Target, Topic Forecast, Actual dates, point-in-time milestone dates.

## 11.4  Freeze Effect on Schedule

- When a project is frozen, schedule time measurement stops.

- Multiple freeze periods can be recorded per project.

- Each freeze period stores: reason, note, start date, end date.

12.  Status Calculation Rules

## 12.1  Milestone Status Values

| Status (Hebrew) | Status (English) | Color Code |
| --- | --- | --- |
| תקין | On Track | Green |
| בסיכון | At Risk | Amber / Orange |
| באיחור | Delayed | Red |
| הושלם | Completed | Blue / Gray |
| לא רלוונטי | Not Relevant | Light Gray |

## 12.2  Domain / Sub-Topic Status

Computed as the worst-performing milestone beneath it.

## 12.3  Main Topic Status — Calculation Algorithm

| Priority | Condition | Resulting Status |
| --- | --- | --- |
| 1 (highest) | Topic actually completed | Completed |
| 2 | Any milestone Delayed OR Topic Forecast is > 7 days late | Delayed |
| 3 | Any milestone At Risk OR Topic Forecast is 1–7 days late | At Risk |
| 4 (default) | None of the above | On Track |

## 12.4  Project Status

Computed as the worst status among Topics 1–5 (Topic 6 excluded).

## 12.5  Deviation Thresholds

| Classification | Condition |
| --- | --- |
| At Risk | Forecast is 1–7 calendar days after target |
| Delayed | Forecast is more than 7 calendar days after target |
| Material Change | Any change > 3 calendar days from previous forecast |

## 12.6  "Requires Management Action" Flag

- Auto-set when project status = Delayed AND the delay has persisted for ≥ 2 weeks.

- Can also be set manually by PMO or PM at any time.

- Manual override is preserved and must be explicitly cleared.

13.  Delay Reasons & Project Freeze

## 13.1  Delay Reason List

| # | Reason (Hebrew) | Reason (English) |
| --- | --- | --- |
| 1 | אישורים / רגולציה | Approvals / Regulation |
| 2 | תכנון | Planning |
| 3 | מכרז / התקשרות | Tender / Procurement |
| 4 | קבלן / ספק | Contractor / Supplier |
| 5 | תקציב / החלטת הנהלה | Budget / Management Decision |
| 6 | תלות בגורם חיצוני | External Dependency |
| 7 | בעיה באתר / בנכס | Site / Asset Issue |
| 8 | שינוי דרישות | Change in Requirements |
| 9 | אחר | Other (note mandatory) |

## 13.2  Freeze Reason List

| # | Reason (Hebrew) | Reason (English) |
| --- | --- | --- |
| 1 | רגולציה / אישורים | Regulation / Approvals |
| 2 | החלטת הנהלה | Management Decision |
| 3 | תקציב | Budget |
| 4 | גורם חיצוני / בעל נכס | External Party / Asset Owner |
| 5 | קבלן / ספק | Contractor / Supplier |
| 6 | אילוץ תפעולי / עסקי | Operational / Business Constraint |
| 7 | אחר | Other (note mandatory) |

📌  When "Other" is selected for either delay or freeze reason, a short free-text note is mandatory.

14.  Contractors

## 14.1  Contractor Domains

| Domain (Hebrew) | Domain (English) | Max per Domain |
| --- | --- | --- |
| בינוי, חשמל ואינסטלציה | Construction, Electrical & Plumbing | 1 lead contractor |
| מיזוג אוויר | HVAC | 1 lead contractor |
| ריהוט | Furniture | 1 lead contractor |
| מיתוג ושילוט | Branding & Signage | 1 lead contractor |

## 14.2  Minimum Rule for Topic 4

📌  Before Topic 4 (Execution) can begin, at least the "Construction, Electrical & Plumbing" contractor must be closed / selected.

15.  Mandatory Update Fields

| Action | Mandatory Fields | Optional Fields |
| --- | --- | --- |
| Mark as Completed | Status = Completed, Actual date | — |
| Mark as At Risk or Delayed | Status, Updated Forecast, Delay Reason | Free-text note |
| Mark as Not Relevant | Status only | — |
| Freeze project | Freeze reason, Start date | Free-text note |
| Select "Other" reason | Free-text note | — |

16.  Key Milestone Logic

## 16.1  Automatic Selection

- Priority: Delayed before At Risk.

- If multiple exist, select the one with the greatest delay.

- If no exception exists: display the current active milestone (open milestone with the nearest target date).

## 16.2  Manual Override

- Both PMO and Project Manager can manually select a key exception milestone.

- Manual selection overrides the auto-selection until cleared.

17.  Screens & Views

📌  All screens are displayed in Hebrew (RTL). UI language is Hebrew only. Terminology in this spec is English for developer reference.

## Screen 1 — Project List / Dashboard

Primary view for all users. Displays all projects in a dense, scannable table.

Columns displayed per project:

| Column (Hebrew) | Column (English) | Source |
| --- | --- | --- |
| קוד | Code | Auto |
| שם | Name | Manual |
| מנהל פרויקט | Project Manager | Manual |
| אחראי נוסף | Additional Owner | Manual |
| סטטוס כללי | Overall Status | Calculated — color-coded badge |
| עדיפות | Priority | Manual — color-coded |
| צפי קבלת נכס | Expected Asset Receipt | Manual |
| יעד אכלוס | Occupancy Target | Manual |
| Forecast אכלוס | Occupancy Forecast | Manual |
| אבן חריגה / פעילה | Exception / Active Milestone | Calculated |
| נדרש טיפול הנהלה | Requires Management Action | Calculated + manual — icon indicator |
| לא עודכן השבוע | Not Updated This Week | Calculated — warning icon |
| מוקפא / פעיל | Frozen / Active | Calculated — badge |

Filter bar (persistent):

- Project Manager (multi-select)

- Status (multi-select)

- Priority (multi-select)

- Requires Management Action (yes/no toggle)

- Not Updated This Week (yes/no toggle)

- Frozen / Active toggle

## Screen 2 — Project Card

Full detail view of a single project.

- Base fields (all project-level data)

- 6 main topics — each showing: Topic target / Forecast / Actual, Status badge

- Milestones under each topic (expandable)

- Freeze history

- Notes log

- Selected contractors

- Last weekly snapshot summary

## Screen 3 — Quick Update

Focused update panel — accessible from Dashboard row or Project Card.

- Milestone status update

- Forecast update

- Actual date entry

- Delay reason selection

- Free-text note

- Toggle "Requires Management Action"

- Manual key exception milestone selection

## Screen 4 — Management Report

Condensed view optimized for weekly management review. One row per project.

| Column | Source |
| --- | --- |
| Project name | Manual |
| Project Manager | Manual |
| Additional owner | Manual |
| Architect | Manual |
| Selected contractors | Structured |
| Priority | Manual |
| Status | Calculated |
| Exception / Active milestone | Calculated |
| Occupancy forecast | Manual |
| Change since last week | Calculated from snapshot |
| Delay reason | Manual |
| Short note | Manual |
| Requires Management Action | Calculated + manual |

## Screen 5 — 30-Day Forward View

Sorted timeline of upcoming milestones and projects requiring immediate action.

- All open milestones with target date within next 30 days

- Sorted by date ascending

- Color-coded by milestone status

- Projects flagged as "Requires Management Action" highlighted at top

## Screen 6 — Default Lists Management (PMO Only)

Admin interface for maintaining all configurable reference lists.

- Planning domains

- Tender domains

- Milestones per topic

- Consultant / designer roles

- Delay reasons

- Freeze reasons

- Contractor / supplier lists

## Screen 7 — User Management (Admin Only)

Accessible only to Admin role.

| Feature | Description |
| --- | --- |
| Pending users list | Shows all users who completed Google Sign-In but are not yet approved |
| Approve user | Activates the account and assigns a role |
| Reject user | Blocks the account; user sees rejection message on login |
| Edit role | Change any user's role at any time |
| Deactivate user | Soft-delete: blocks access but preserves audit data |
| Project reassignment | Reassign a PM's projects to another user on deactivation |
| User list | Full list with: name, email, role, last login, status (active / pending / deactivated) |

18.  Weekly Snapshot

Only PMO (and Admin) can perform week close and save a snapshot.

## 18.1  Snapshot Content (Minimum)

| Field Captured | Source |
| --- | --- |
| Project status | Calculated |
| Occupancy forecast | Manual / last updated |
| Key exception milestone | Calculated / manual |
| Requires Management Action flag | Calculated + manual |
| Not Updated This Week flag | Calculated |

## 18.2  Usage

- Screen 4 (Management Report) uses the latest snapshot to calculate "Change since last week".

- Screen 2 (Project Card) displays the last snapshot as a summary panel.

19.  Design System (UI/UX)

## 19.1  Core Principle

The entire interface is Hebrew-first, RTL (Right-to-Left) layout. Every screen, label, button, tooltip, validation message, and notification is in Hebrew. There is no toggle to English. Developers reference this specification in English; the deployed product is 100% Hebrew.

## 19.2  Layout & Direction

- HTML direction: dir="rtl" on <html> and <body>

- Flexbox / Grid: all row directions reversed (flex-direction: row-reverse or logical properties)

- Text alignment: text-align: right as base default

- Icons: directional icons (chevrons, arrows) must be mirrored for RTL context

- Tables: first column is rightmost

- Navigation sidebar: positioned on the right

## 19.3  Color System

| Token | Hex | Usage |
| --- | --- | --- |
| --color-primary | #1B3A5C | Main nav, headers, primary actions |
| --color-secondary | #2E6DA4 | Subheadings, links, secondary actions |
| --color-accent | #E8834A | Key CTAs, notifications, highlights |
| --color-surface | #F5F8FC | Page background |
| --color-card | #FFFFFF | Card / panel backgrounds |
| --color-border | #D0D7DE | Dividers, table borders |
| --color-text-primary | #1A202C | Main body text |
| --color-text-secondary | #4A5568 | Captions, meta text |
| --status-on-track | #1A7F4B | Green — On Track |
| --status-at-risk | #C05621 | Amber — At Risk |
| --status-delayed | #C53030 | Red — Delayed |
| --status-completed | #2E6DA4 | Blue — Completed |
| --status-frozen | #718096 | Gray — Frozen |
| --status-not-relevant | #CBD5E0 | Light gray — Not Relevant |

## 19.4  Typography

| Element | Font | Size | Weight |
| --- | --- | --- | --- |
| Page heading (H1) | Rubik or Heebo | 24px | 700 |
| Section heading (H2) | Rubik or Heebo | 18px | 600 |
| Sub-heading (H3) | Rubik or Heebo | 15px | 600 |
| Body text | Rubik or Heebo | 14px | 400 |
| Table cell | Rubik or Heebo | 13px | 400 |
| Badge / label | Rubik or Heebo | 11px | 600 uppercase |
| Caption / meta | Rubik or Heebo | 12px | 400 |

📌  Rubik and Heebo are both Google Fonts designed specifically for Hebrew + Latin rendering. Use Rubik as primary; fall back to Heebo.

## 19.5  Status Badges

Status is always shown as a colored pill badge with a short Hebrew label. Never use color alone without the text label.

| Status | Hebrew Label | Badge Color | Text Color |
| --- | --- | --- | --- |
| On Track | תקין | Green (#1A7F4B) | White |
| At Risk | בסיכון | Amber (#C05621) | White |
| Delayed | באיחור | Red (#C53030) | White |
| Completed | הושלם | Blue (#2E6DA4) | White |
| Frozen | מוקפא | Gray (#718096) | White |
| Not Relevant | לא רלוונטי | Light gray (#CBD5E0) | Dark gray |

## 19.6  Key UX Principles

- Minimal required fields — forms ask only what is essential.

- Short forms — no multi-step wizards except project creation.

- Inline editing where possible — minimize modal dialogs.

- Confirmation dialogs only for destructive actions (freeze, delete, deactivate user).

- Status badges must be colorblind-safe — include icon + text, not color only.

- Dense information layout preferred in dashboard — management needs to scan 50 projects rapidly.

- Mobile-responsive is desired but desktop-first in Phase 1.

## 19.7  Accessibility

- WCAG 2.1 Level AA target

- All interactive elements keyboard-navigable

- ARIA labels on all icon-only buttons

- Minimum contrast ratio 4.5:1 for body text

20.  Phase 2 Backlog

The following features are explicitly deferred to Phase 2. They must not delay Phase 1 delivery.

| Feature | Notes |
| --- | --- |
| Automated alerts / notifications | E.g. email when milestone turns Delayed |
| Full audit trail (who changed what and when) | Phase 1 logs writes but does not expose UI |
| Template versioning | Phase 1 has a single live template |
| Schedule template at milestone level | Phase 1 only at main-topic level |
| Complex dependency chain calculations | Phase 1 is manual scheduling only |
| Mandatory justification for every manual change | Phase 1: optional notes |
| Mandatory reason for "Not Relevant" selections | Phase 1: no reason required |
| External stakeholder access (read-only portal) | Contractors, architects, etc. |
| Advanced reports & analytics | Charts, trend analysis, export to Excel/PDF |
| Integrations (ERP, BIM, etc.) | Out of scope entirely for Phase 1 |
| Budget & financial tracking | Separate system or Phase 2+ |
| Document management | Separate DMS or Phase 2+ |

End of Specification — Phase 1

Next deliverables: ERD / Data Model  ·  Wireframes for 7 screens  ·  Detailed calculation rules